## Cover
TEST PLAN
Project Name | TheGioiDiDong |  |  | Reviewer | Nguyễn Hoàng Đạt
Project Code | TGDD |  |  | Review date | 31/12/2024
Creator | Nguyễn Xuân Thành Trung |  |  | Approver
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-30 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Payment_Testplan
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Define test objectives and scope | Test Manager | Define clear objectives aligned with course requirements
| 2 | Design and prepare test cases and test data | Test Analyst/QA Team | Create detailed test cases with expected results
| 3 | Perform test execution | QA Team | Execute tests systematically and document results
| 4 | Report and categorize defects | QA Team | Log and prioritize defects based on severity
| 5 | Review and validate test results | QA Lead, Stakeholders | Ensure test coverage meets requirements
| 6 | Conduct exploratory testing | QA Team | Identify additional issues through unscripted testing
| 7 | Provide a summary report and recommendations | Test Manager | Create comprehensive report with findings and improvements
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Test Case Identification | Use clear naming convention for easy reference
| 2 | Test Case Structure | Include prerequisites, steps, and expected results
| 3 | Traceability | Link test cases to specific requirements
| 4 | Prioritization | Organize test cases by importance
| 5 | Reusability | Design test cases that can be reused
| 6 | Clarity and Conciseness | Write clear and easy-to-follow test cases
| 7 | Review and Approval Process | Team review of test cases for quality assurance
Quality metric
Description of target
| # | Items | Target | Note
| 1 | Defect Detection | 80% of defects found during testing | Track effectiveness of testing process
| 2 | Test Coverage | Minimum 85% coverage | Test majority of application features
| 3 | Defect Resolution | Fix critical defects within 24 hours | Ensure quick resolution of major issues
| 4 | Test Case Quality | 90% pass rate for reviewed test cases | Maintain high quality of test cases
| 5 | Test Execution Rate | Complete 85% of planned tests | Track testing progress
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | Critical defects resolved | High | All critical issues must be fixed
| 2 | Test coverage achieved | High | Meet minimum coverage requirements
| 3 | No high-priority defects | High | Resolve all major issues
| 4 | Requirements validated | Medium | Verify all main features work
| 5 | Documentation complete | Medium | All test documents finalized
| 6 | Instructor approval | High | Get final approval for completion
| 7 | Match requirements | High | Ensure alignment with project specs
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
|  | Critical blocking issues | Stop testing if major blocking issues are found
|  | Resource unavailability | Pause if team members are unavailable
|  | Requirement changes | Suspend if significant changes occur
|  | Incomplete documentation | Pause if test cases need updates
|  | Major system issues | Stop if system is unstable
| # | Resumption Requirements | Note
|  | Critical issues fixed | Resume after blocking issues resolved
|  | Resources available | Ensure team members are available
|  | Updated documentation | Test cases and plans updated
|  | Issue analysis complete | Understanding of what caused suspension
|  | Team approval | Team agrees to resume testing

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Develop test plan for application features including: Shopping Cart, News, Product Search, Product Information Viewing, and Payment/Order Placement |  | Leader / Testers | Ensure alignment with course requirements
2 | Create test design | Design test approaches for each feature, including functional and non-functional testing |  | Tester | Include both manual and automated testing
3 | Create test cases | Write detailed test cases for all features, including positive and negative scenarios |  | Tester | Use standardized test case template
4 | Create test data | Prepare test data for test cases, including valid and invalid data |  | Tester | Ensure coverage of all test scenarios
5 | Execute system test | Perform system testing for all features |  | Tester | Document detailed test results
6 | Defects list | Create list of defects found during testing |  | Tester | Classify defect severity
7 | Create test report | Create summary report of testing process and results |  | Leader / Testers | Include analysis and recommendations
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 30/09/2024 | Test leader | Test manager, Team | This document
2 | Test cases | 31/10/2024 | Test leader | Test manager, Team | Include test matrix
3 | Defect logs | 15/12/2024 | Test leader | Test manager, Team | Include defect classification
4 | Test report | 31/12/2024 | Test leader | Test manager, Team | Include evaluation and conclusions
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Test Planning | Use Agile method for phase-based test planning |  |  | Adjust plan based on feedback
2 | Test Execution | Use test case management tools to track execution |  |  | Allow parallel testing
3 | Defect Management | Use defect tracking system to record and classify defects |  |  | Regular defect review meetings
4 | Reporting and Metrics | Create periodic reports on test progress and defect count |  |  | Provide statistical data
5 | Team Collaboration | Daily team meetings to update progress and discuss issues |  |  | Ensure all members understand tasks
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack testing experience |  | Organize group study and knowledge sharing |  | 1. Study documentation 2. Learn from experienced members 3. Practice extensively
2 | Code changes affecting tests |  | Monitor code changes closely |  | 1. Contact development team 2. Update test cases 3. Allocate time for retesting
3 | Tight project timeline |  | Prioritize testing of critical features |  | 1. Distribute work efficiently 2. Work in parallel 3. Focus on main test cases
4 | Misunderstanding requirements |  | Regular requirement reviews with team |  | 1. Organize team meetings 2. Review documentation 3. Consult instructor when needed
5 | Reduced productivity after holidays |  | Create backup plans |  | 1. Adjust schedule 2. Reassign tasks 3. Increase work intensity
6 | Incomplete testing |  | Review requirements thoroughly and create test checklist |  | 1. Review test coverage 2. Add test cases 3. Cross-check testing
7 | Changing requirements |  | Be flexible in updating test plans |  | 1. Analyze impact 2. Update test documents 3. Retest affected areas
Assumption
Listing of all assumption of test process.
# | Type | Description
1 | Resources | Team members will participate fully and on schedule
2 | Requirements | Basic requirements will remain relatively stable
3 | Test Environment | Test environment will be properly prepared for testing
4 | Support | Instructor and other teams will provide support when needed
5 | Skills | Instructor and other teams will provide support when needed
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1 | Testing Techniques | Learn basic and advanced testing techniques |  | Test Lead | 2024-10-01 | 30/09/2024
2 | Defect Management Tools | Guide on using defect management and reporting tools |  | Test Lead | 2024-10-01 | 31/10/2024
3 | Performance Testing | Learn performance testing and result analysis |  | QA Specialist | 2024-10-01 | 15/12/2024
4 | Test Case Writing | Effective test case writing techniques |  | Test Lead | 2024-10-01 | 31/12/2024
Note on E34: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G34: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B45: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the ProlTM system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | Payment_Testplan
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone
OS | Window 10/Window 11 Mac Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | Edge, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 19130031 Nguyễn Hoàng Đạt | Leader | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Cart] functionality.
2 | 20130222 Cao Thành Đạt | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Search] functionality.
3 | 21130371 Trần Minh Hướng | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Information Viewing] functionality.
4 | 20130242 Nguyễn Văn Giang | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [News] functionality.
5 | 20130452 Nguyễn Xuân Thành Trung | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Payment/Order Placement] functionality.
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-19 | 2024-10-26
2 | Create test design | 2024-10-27 | 2024-10-31
3 | Create test case | 2024-11-01 | 2024-11-09
4 | Execute test and log bugs | 2024-11-10 | 2024-11-23
5 | Evaluting exit criteria & Test report | 2024-11-24 | 2024-12-20
6 | Review | 2024-12-28 | 2024-12-28
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 7
| Create test design | 7 | 4
| Create test case | 11 | 8
| Execute test and log bugs | 19 | 13
| Evaluting exit criteria & Test report | 32 | 26
| Review | 65 | 1
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October | [12 empty] | November | [29 empty] | December
|  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: October 19
2 | Create test design | bar: October 27
2024-01-02 | News | 20130242_Nguyễn Văn Giang | bar: October 27
2024-02-02 | Product Search | 20130222_Cao Thành Đạt
2024-03-02 | Product Information Viewing | 21130371_Trần Minh Hướng
2024-04-02 | Payment/Order Placement | 20130452_Nguyễn Xuân Thành Trung
2024-05-02 | Shopping Cart | 19130031_Nguyễn Hoàng Đạt
2024-06-02 | Review | Team | bar: October 30
3 | Create test case | bar: November 1
2019-01-03 | News | 20130242_Nguyễn Văn Giang | bar: November 1
2019-02-03 | Product Search | 20130222_Cao Thành Đạt
2019-03-03 | Product Information Viewing | 21130371_Trần Minh Hướng
2019-04-03 | Payment/Order Placement | 20130452_Nguyễn Xuân Thành Trung
2019-05-03 | Shopping Cart | 19130031_Nguyễn Hoàng Đạt
2019-06-03 | Review | Team | bar: November 8
4 | Execute test and logs bug | bar: November 10
2019-01-04 | News | 20130242_Nguyễn Văn Giang | bar: November 10
2019-02-04 | Product Search | 20130222_Cao Thành Đạt
2019-03-04 | Product Information Viewing | 21130371_Trần Minh Hướng
2019-04-04 | Payment/Order Placement | 20130452_Nguyễn Xuân Thành Trung
2019-05-04 | Shopping Cart | 19130031_Nguyễn Hoàng Đạt
2019-06-04 | Review | Team | bar: November 22
5 | Evaluting exit criteria & Test report | Team | bar: November 24
2024-01-05 | Check, adjust, and finalize the summary | Team | bar: December 21
6 | Review | Team | bar: December 28

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
STT | Members
1 | 20130242_Nguyễn Văn Giang
2 | 20130222_Cao Thành Đạt
3 | 21130371_Trần Minh Hướng
4 | 20130452_Nguyễn Xuân Thành Trung
5 | 19130031_Nguyễn Hoàng Đạt