## Cover
TEST PLAN
Project Name | TheGioiDiDong |  |  | Reviewer | Nguyễn Hoàng Đạt
Project Code | TGDD |  |  | Review date | 2024-10-30
Creator | Cao Thành Đạt |  |  | Approver | Nguyễn Minh Hướng
Version | v1.0 |  |  | Approval Date | 2024-10-31
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-30 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | 20130222_Testplan
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Define test objectives and scope | Test Manager | Define clear success criteria
| 2 | Design and prepare test cases and test data | Test Analyst/QA Team | Create detailed documentation for each test case, including expected outcomes
| 3 | Perform test execution | QA Team | Execute tests in a controlled environment and record findings
| 4 | Report and categorize defects | QA Team | Use a systematic approach for logging defects and prioritizing them based on severity
| 5 | Review and validate test results | QA Lead, Stakeholders | Ensure all requirements are adequately covered by test cases
| 6 | Conduct exploratory testing | QA Team | Discover unexpected issues and assess user experience beyond scripted tests
| 7 | Provide a summary report and recommendations | Test Manager | Compile a comprehensive report including lessons learned and suggested improvements
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Test Case Identification | Clearly identify and name test cases for easy understanding
| 2 | Test Case Structure | Follow a standard format that includes sections like test objectives, preconditions, and expected results
| 3 | Traceability | Ensure each test case can be linked to corresponding requirements for completeness
| 4 | Prioritization | Classify test cases by priority to optimize testing resources
| 5 | Reusability | Design test cases to be reusable in future projects or different versions of the product
| 6 | Clarity and Conciseness | Test cases should be written concisely and clearly, avoiding unnecessary information
| 7 | Review and Approval Process | Establish a review and approval process for test cases to ensure accuracy and feasibility
Quality metric
Description of target
| # | Items | Target | Note
| 1 | Defect Density | Less than 1 defect per 1000 lines of code | Measure the number of defects relative to the size of the codebase
| 2 | Test Coverage | At least 90% coverage | Ensure that a minimum of 90% of requirements and code paths are tested
| 3 | Defect Resolution Time | Average resolution within 48 hours | Track the average time taken to resolve defects after they are reported
| 4 | Customer Satisfaction | Target score of 4.5/5 | Gather feedback from customers to measure satisfaction with the product quality
| 5 | Test Automation Rate | 70% of test cases automated | Increase the percentage of test cases that are automated to improve efficiency
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | All critical defects must be resolved | High | Critical defects should be fixed before release to ensure product quality
| 2 | Test coverage meets the required threshold | High | Ensure at least 90% of functional requirements are tested
| 3 | No high-severity defects remain open | High | All high-severity defects should be addressed before sign-off
| 4 | Acceptance criteria for each requirement are met | Medium | Each requirement should be validated according to its acceptance criteria
| 5 | Documentation is complete and reviewed | Medium | Ensure all testing documentation is finalized and approved
| 6 | Stakeholder approval is obtained | High | Final approval from stakeholders is necessary to confirm the release readiness
| 7 | Software is correct with SRS | High
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
|  | Critical defects are discovered | If critical defects are found that prevent further testing, the process must be paused until they are resolved
|  | Lack of resources | Testing must be suspended if necessary resources (e.g., personnel, test environments) are unavailable
|  | Changes in project scope or requirements | If significant changes occur that impact the test plan, testing should be paused for re-evaluation
|  | Inadequate documentation | Testing should be suspended if necessary documentation (test cases, requirements) is incomplete or unclear
|  | Severe performance issues | If severe performance issues are identified during testing, it may require a pause to address underlying causes
| # | Resumption Requirements | Note
|  | All critical defects must be resolved | Testing can only resume after all critical defects are fixed and verified.
|  | Availability of necessary resources | Ensure all required resources (personnel, tools, environments) are in place before resuming testing activities
|  | Updated test plan and scope | The test plan must be revised to reflect any changes in requirements or scope before testing resumes
|  | Completion of root cause analysis | A thorough analysis of any issues that led to the suspension must be completed before resuming
|  | Approval from stakeholders | Obtain necessary approvals from stakeholders to confirm it is appropriate to resume testing

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Develop a comprehensive plan outlining the testing strategy and objectives for the application, including features such as Shopping Cart, News, Product Search, Product Information Viewing, and Payment/Order Placement |  | Leader / Testers | Ensure alignment with project goals
2 | Create test design | Design the overall approach to testing, focusing on functional testing for the identified features |  | Tester | Include methods for both manual and automated testing
3 | Create test cases | Develop detailed test cases that cover all functionalities including the Shopping Cart, News, Product Search, Product Information Viewing, and Payment/Order Placement |  | Tester | Follow standard formats and best practices
4 | Create test data | Prepare necessary data for executing test cases, ensuring it covers all scenarios related to the functionalities |  | Teseter | Include valid and invalid data sets
5 | Execute system test | Carry out system testing for all functionalities mentioned above, ensuring each is validated |  | Teseter | Log any issues or defects encountered
6 | Defects list | Maintain a list of all defects identified during testing, categorized by severity |  | Teseter | Regularly update and prioritize defects for resolution
7 | Create test report | Compile a final report summarizing testing activities, results, and recommendations for each functionality tested |  | Leader / Testers | Include insights and lessons learned for future testing
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-12-31 | Test leader | Test manager, Team | This document itself
2 | Test cases | 2024-12-31 | Test leader | Test manager, Team
3 | Defect logs | 2024-12-31 | Test leader | Test manager, Team
4 | Test report | 2024-12-31 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Test Planning | Utilize agile methodologies to define testing scope and objectives, incorporating continuous feedback |  |  | Ensures alignment with project goals and adaptability
2 | Test Execution | Implement test case management tools for efficient execution and tracking of test cases and defects |  |  | Improves visibility and collaboration among team members
3 | Defect Management | Use a defect tracking system to log, categorize, and prioritize defects based on severity and impact |  |  | Facilitates timely resolution and communication with stakeholders
4 | Reporting and Metrics | Generate regular test reports with key metrics such as test coverage, defect density, and test execution status |  |  | Provides insights into testing progress and areas for improvement
5 | Team Collaboration | Hold daily stand-up meetings to discuss progress, challenges, and next steps among team members |  |  | Promotes transparency and swift resolution of issues
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
6 | Inadequate test coverage |  | Perform thorough requirement analysis and review to ensure all functionalities are covered |  | Increase test case development resources to fill coverage gaps quickly
7 | Changing requirements |  | Maintain open communication with stakeholders to understand and document any changes promptly |  | Adjust the test plan and test cases to reflect changes and ensure all updates are tested
Assumption
Listing of all assumption of test process.
# | Type | Description
1 | Resource Availability | All necessary resources (team members, tools, and environments) will be available for the testing process as planned
2 | Requirement Stability | Requirements will remain stable throughout the testing phase, minimizing changes to the test plan and test cases
3 | Test Environment | The test environment will closely mirror the production environment, ensuring that tests provide accurate results
4 | Training and Knowledge | Stakeholders will provide timely feedback and support for any issues encountered during testing
5 | Stakeholder Engagement | Team members will have the necessary training and understanding of the application and testing tools to execute tests effectively
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1 | Test Automation | Training on automation tools and frameworks used for testing, focusing on scripting and execution |  | Test Lead | 2024-10-01 | 2024-10-15
2 | Defect Management Tools | Overview of defect tracking tools, including how to log, categorize, and prioritize defects effectively |  | Test Lead | 2024-10-01 | 2024-10-15
| Performance Testing | Training on performance testing techniques and tools, focusing on load testing and analysis of results |  | QA Specialist | 2024-10-01 | 2024-10-15
3 | Test Case Design Techniques | Workshop on creating effective test cases, including boundary value analysis and equivalence partitioning |  | Test Lead | 2024-10-01 | 2024-10-15
Note on E34: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G34: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B45: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the ProlTM system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | 20130222_Testplan
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 19130031 Nguyễn Hoàng Đạt | Leader | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Cart] functionality.
2 | 20130222 Cao Thành Đạt | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Search] functionality.
3 | 21130371 Trần Minh Hướng | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Information Viewing] functionality.
4 | 20130242 Nguyễn Văn Giang | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [News] functionality.
5 | 20130452 Nguyễn Xuân Thành Trung | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Payment/Order Placement] functionality.
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-19 | 2024-10-26
2 | Create test design | 2024-10-27 | 2024-10-31
3 | Create test case | 2024-11-01 | 2024-11-09
4 | Execute test and log bugs | 2024-11-10 | 2024-11-23
5 | Evaluting exit criteria & Test report | 2024-11-24 | 2024-12-20
6 | Review | 2024-12-28 | 2024-12-28
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 7
| Create test design | 7 | 4
| Create test case | 11 | 8
| Execute test and log bugs | 19 | 13
| Evaluting exit criteria & Test report | 32 | 26
| Review | 65 | 1
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October | [12 empty] | November | [29 empty] | December
|  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: October 19
2 | Create test design | bar: October 27
2024-01-02 | News | 20130242 Nguyễn Văn Giang | bar: October 27
2024-02-02 | Product Search | 20130222 Cao Thành Đạt
2024-03-02 | Product Information Viewing | 21130371 Trần Minh Hướng
2024-04-02 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2024-05-02 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2024-06-02 | Review | Team | bar: October 30
3 | Create test case | bar: November 1
2019-01-03 | News | 20130242 Nguyễn Văn Giang | bar: November 1
2019-02-03 | Product Search | 20130222 Cao Thành Đạt
2019-03-03 | Product Information Viewing | 21130371 Trần Minh Hướng
2019-04-03 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2019-05-03 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2019-06-03 | Review | Team | bar: November 8
4 | Execute test and logs bug | bar: November 10
2019-01-04 | News | 20130242 Nguyễn Văn Giang | bar: November 10
2019-02-04 | Product Search | 20130222 Cao Thành Đạt
2019-03-04 | Product Information Viewing | 21130371 Trần Minh Hướng
2019-04-04 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2019-05-04 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2019-06-04 | Review | Team | bar: November 22
5 | Evaluting exit criteria & Test report | Team | bar: November 24
2024-01-05 | Check, adjust, and finalize the summary | Team | bar: December 21
6 | Review | Team | bar: December 28

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
# | Term | Definition/explanation
1 | TGDD | Abbreviation for Thế Giới Di Động, the e-commerce website being tested
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | Đặng Văn Đa
2 | Nguyễn Hoàng Vũ
3 | 13130154_Nguyễn Huỳnh Gia Đạt