## Cover
TEST PLAN
Project Name | TestCase_TheGioiDiDong |  |  | Reviewer | Cao Thành Đạt
Project Code | TGDD |  |  | Review date | 2024-11-01
Creator | Nguyễn Hoàng Đạt |  |  | Approver | Nguyễn Văn Giang
Version | v0.1 |  |  | Approval Date | 2024-10-31
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-30 | v0.1 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | 19130031_Testplan
Test Policy | - General Policy: Adopts a standard testing process, including test case design and test data preparation. - Requirements to Test / Not to Test: + To Test: Product search functions, shopping cart, ordering process. + Not to Test: Non-core features and infrequently used interfaces. - Exit Criteria: All major test cases are completed, with no critical issues remaining. - Suspension and Resumption Criteria: Testing is paused if system errors or critical features are identified; resumed once these issues are resolved.
Test Management | - Scope: Testing core functions of TGDD, including ordering, shopping cart, and product search. - Deliverables: Test plan, test cases, defect reports, and test summary report. - Management Method: Agile testing approach with issue tracking on GitHub. - Risks: + Schedule risk if unexpected system issues arise. + Lack of clear requirements from the client. - Assumptions: System stability with minimal changes during testing. - Training Plan: Basic training on TGDD features to be tested and instruction on defect tracking.
Test Strategy | - Test Levels and Types: + Unit testing for core modules. + Integration testing across features. + System testing for the entire website. + Acceptance testing to validate product meets requirements. - Test Environment: Desktop and mobile devices using major browsers. - Test Data: Simulated user scenarios and test data.
Master Schedule | Team Introduction and Assignment: Includes testers and project manager. Main Schedule: -Week 1: Prepare test plan and design test cases. -Weeks 2 - 3: Execute testing. -Week 4: Compile and report test results.
Appendix | - Detailed Definitions of Test Levels, Types, and Techniques: Attached list of test levels, types (functional, UI, security). - Terminologies and Definitions: Glossary of terms used in the plan (e.g., test case, test plan, defect). |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
19130031_TestDesign |  |  |  | 0.1

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Define test objectives and scope | Test Manager | Establish primary goals
| 2 | Design and prepare test cases and test data | Test Analyst/QA Team | Follow standard formats
| 3 | Execute test cases | QA Team | Document each result
| 4 | Log and track defects | Test Manager/QA Team | Use defect tracking tool
| 5 | Review and validate test results | QA Lead, Stakeholders | Ensure requirement coverage
| 6 | Manage test environment and data | Environment Specialist | Refresh before testing
| 7 | Provide test summary and final report | Test Manager | Compile post-testing review
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Test cases must be derived from requirements | Ensure traceability between requirements and test cases.
| 2 | Each test case must have a unique identifier | Facilitates easy tracking and reference.
| 3 | Test cases should include preconditions and postconditions | Clearly define the setup and expected outcomes.
| 4 | Test cases must cover both positive and negative scenarios | Ensures robustness in testing.
| 5 | Test cases should be reviewed and approved | Involve stakeholders for validation before execution.
| 6 | Use clear and concise language in test case descriptions | Enhances readability and understanding for all testers.
| 7 | Maintain a balance between manual and automated test cases | Optimize efficiency while ensuring comprehensive coverage.
| 8 | Regularly update test cases to reflect changes in requirements | Keep the testing suite relevant and effective.
| 9 | Ensure test cases are executable and reproducible | Test cases should be feasible to run multiple times with consistent results.
| 10 | Document any assumptions made during test case design | Helps in understanding the context of the tests.
Quality metric
Description of target
| # | Items | Target | Note
| 1 | Defect Density | Less than 1 defect per 100 lines of code | Measures the number of defects relative to the size of the codebase.
| 2 | Test Coverage | At least 90% functional coverage | Ensures most of the application is tested.
| 3 | Test Case Pass Rate | 95% or higher | Indicates the effectiveness of test cases in identifying defects.
| 4 | Customer-reported Issues | Less than 5% of total defects | Reflects the quality from the end-user perspective.
| 5 | Mean Time to Detect Defects | Within 2 days of introduction | Measures the efficiency of the testing process.
| 6 | Mean Time to Resolve Defects | Within 5 days of detection | Indicates how quickly issues are addressed.
| 7 | Requirement Stability Index | 90% stable requirements | Measures changes to requirements during testing.
| 8 | Automated Test Ratio | 70% of tests automated | Reflects the balance between manual and automated testing efforts.
| 9 | Test Execution Efficiency | 80% tests executed on schedule | Indicates adherence to testing timelines.
| 10 | User Satisfaction Score | 85% satisfaction or higher | Measures the quality of the product from the user's viewpoint.
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | All critical defects are resolved | High | Must be fixed before release.
| 2 | Test case pass rate is ≥ 95% | High | Ensures high reliability of the application.
| 3 | No high-severity defects open at release | High | Only low or medium-severity defects may remain.
| 4 | Test coverage is at least 90% | Medium | Ensures that most of the functionality is tested.
| 5 | User acceptance testing is completed | High | Final confirmation from end-users that the product meets requirements.
| 6 | Performance metrics meet defined targets | Medium | Application should perform within acceptable limits.
| 7 | Documentation is complete | Low | User manuals and support documents are prepared and approved.
| 8 | All functional requirements are validated | High | Ensures that the product meets all specified requirements.
| 9 | Automated test execution success rate ≥ 90% | Medium | Confirms reliability and efficiency of automated tests.
| 10 | No critical issues reported post-deployment | High | The product should function without critical issues after launch.
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | Critical defects identified during testing | Must be addressed before testing can continue.
| 2 | Resource unavailability | If key personnel are unavailable, testing will be paused.
| 3 | Environment issues | If the test environment is unstable or unavailable.
| 4 | Incomplete requirements | If requirements are unclear or incomplete, testing must stop.
| 5 | Major changes in application functionality | If significant changes occur, a review and pause are needed.
| # | Resumption Requirements | Note
| 1 | All critical defects must be resolved | Ensure that all critical defects are addressed before resuming.
| 2 | Test environment must be stable | The testing environment must be verified as functional and stable.
| 3 | Availability of key personnel | Required team members must be available to resume testing.
| 4 | Updated requirements must be clarified | Any unclear requirements should be reviewed and clarified.
| 5 | Approval from stakeholders | Testing can resume only after stakeholders approve the plan to continue.

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of TGDD website system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | 19130031_TestDesign
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1 | Test Case | A set of conditions or actions used to verify a particular functionality or feature works as intended.
2 | Pass/Fail Criteria | Conditions determining whether a test case has succeeded or failed based on expected results.
3 | Suspension Criteria | Conditions that require the testing process to pause until the issues are resolved.
4 | Resumption Requirements | Conditions to be met in order to resume paused test activities.
5 | Quality Metric | Standards or measures used to assess the effectiveness or quality of the test process.
6 | Exit Criteria | The requirements that must be met to conclude the testing phase.
7
8
9
10
11
12
13
14
15
16
Glossary
# | Term | Definition/Explanation
1 | TGDD | Abbreviation for Thế Giới Di Động, the e-commerce website being tested.
2 | Environment | Setup or configuration of software, hardware, and network used during testing.
3
4
5
6
Members
1 | 20130242 Nguyễn Văn Giang
2 | 20130222 Cao Thành Đạt
3 | 21130371 Trần Minh Hướng
4 | 20130452 Nguyễn Xuân Thành Trung
5 | 19130031 Nguyễn Hoàng Đạt

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Develop the overall test plan and strategy. |  | Team | Defines scope and objectives.
2 | Create test design | Design the structure and criteria for tests. |  | Team | Based on product requirements.
3 | Create test cases | Define individual test cases for execution. |  | Team | Detailed test steps and expected outcomes.
4 | Create test data | Prepare necessary data for testing scenarios. |  | Team | Includes both valid and invalid data sets.
5 | Execute system test | Conduct testing across the entire system. |  | Team | Includes functional and non-functional testing.
6 | Defects list | Record and track defects identified in testing. |  | Team | Logged in defect management tool.
7 | Create test report | Summarize findings, results, and recommendations. |  | Team | Finalized after test completion.
8 | Shopping Cart | Testing adding, removing, and updating items within the shopping cart. |  | Leader | Includes both desktop and mobile testing for cart behavior.
9 | News | Testing functionalities related to viewing, filtering, and accessing news articles. |  | Members | Includes news loading speed and formatting consistency.
10 | Product Search | Verifying product search functionality by keywords, categories, and filters. |  | Members | Ensure relevance and accuracy of search results.
11 | Product Information Viewing | Testing access to and display of product details, including descriptions, specifications, and images. |  | Members | Validate accurate and complete product information.
12 | Payment/Order Placement | Testing order placement process, including payment methods and order confirmation. |  | Members | Ensure payment integrations are functional.
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-12-28 | Test leader, Team | Test manager | This document itself
2 | Test cases | 2024-12-28 | Test leader, Team | Test manager | The Test design document "19130031_TestDesign"
3 | Test report | 2024-12-28 | Test leader, Team | Test manager | The Test design document "19130031_TestDesign"
4 | Test Design Document | 2024-12-28 | Test leader, Team | Test manager | The Test design document "19130031_TestDesign"
5 | Defects List | 2024-12-28 | Test leader, Team | Test manager | Tracks issues found during testing.
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Test Planning | Define testing scope and objectives, assign roles, estimate time and resources. |  |  | Ensures alignment on goals.
2 | Test Execution | Run test cases according to priority, track progress in real-time, and adjust based on any blockers. |  |  | Daily progress reports.
3 | Defects Management | Use a bug-tracking tool (e.g., JIRA) to log and monitor defects, assigning severity and priority. |  |  | Prioritize critical issues.
4 | Test Reporting | Create daily summaries and a final test report, including metrics on pass rates and defect density.
5 | Communication | Weekly meetings for updates, Slack channel for daily check-ins, email for significant milestones. |  |  | Clear channels for updates.
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Schedule testing in phases to balance resource load |  | Reallocate resources or extend deadlines
6 | Delays in requirement changes impacting test cases |  | Set a freeze date for requirements |  | Update critical test cases only
7 | Key team member unavailability (e.g., due to illness) |  | Cross-train team members |  | Reassign tasks among available team members
8 | Defects blocking test progression |  | Prioritize and fast-track bug fixing |  | Work on non-blocked test areas while waiting
9 | Test environment instability or outages |  | Regularly back up environment |  | Shift testing to alternative environments
10 | Delayed availability of test data |  | Use mock or similar historical data |  | Prepare test cases that don’t need specific data
Assumption
Listing of all assumption of test process.
# | Type | Description
1 | Timeline | The testing schedule will be executed as planned without delays.
2 | Technical | The tools and techniques used for testing will be effective and suitable for project requirements.
3 | Resources | All necessary resources for the testing process (staff, equipment, environment) will be available on time.
4 | Requirements | The requirements provided by the client will be complete and accurate for conducting tests.
5 | Support | The development team will provide timely support during the testing process, especially when issues arise.
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1 | Performance Testing | Techniques for testing application performance |  | Performance Tester | 2024-10-01 | 2024-10-18
2 | Test case design | Techniques for writing effective test cases |  | Senior Tester | 2024-10-01 | 2024-10-18
3 | Defect tracking | Process for logging, tracking, and managing defects |  | Tester Lead | 2024-10-01 | 2024-10-18
4 | Software Testing Fundamentals | Overview of software testing principles and practices |  | Test Manager | 2024-10-01 | 2024-10-18

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 19130031 Nguyễn Hoàng Đạt | Leader | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Cart] functionality.
2 | 20130222 Cao Thành Đạt | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Search] functionality.
3 | 21130371 Trần Minh Hướng | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Product Information Viewing] functionality.
4 | 20130242 Nguyễn Văn Giang | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [News] functionality.
5 | 20130452 Nguyễn Xuân Thành Trung | Member | Read and Analyze Document, Test Design, Test Cases, Execute Test Cases, and Log Bugs for the [Payment/Order Placement] functionality.
Detail Schedule
Link - Detail Schedule
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-19 | 2024-10-26
2 | Create test design | 2024-10-27 | 2024-10-31
3 | Create test case | 2024-11-01 | 2024-11-09
4 | Execute test and log bugs | 2024-11-10 | 2024-11-23
5 | Evaluting exit criteria & Test report | 2024-11-24 | 2024-12-20
6 | Review | 2024-12-28 | 2024-12-28
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 7
| Create test design | 7 | 4
| Create test case | 11 | 8
| Execute test and log bugs | 19 | 13
| Evaluting exit criteria & Test report | 32 | 26
| Review | 65 | 1

## Detail Schedule
# | Item | Responsibilities | October | [12 empty] | November | [29 empty] | December
|  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: October 19
2 | Create test design | bar: October 27
2024-01-02 | News | 20130242 Nguyễn Văn Giang | bar: October 27
2024-02-02 | Product Search | 20130222 Cao Thành Đạt
2024-03-02 | Product Information Viewing | 21130371 Trần Minh Hướng
2024-04-02 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2024-05-02 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2024-06-02 | Review | Team | bar: October 30
3 | Create test case | bar: November 1
2019-01-03 | News | 20130242 Nguyễn Văn Giang | bar: November 1
2019-02-03 | Product Search | 20130222 Cao Thành Đạt
2019-03-03 | Product Information Viewing | 21130371 Trần Minh Hướng
2019-04-03 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2019-05-03 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2019-06-03 | Review | Team | bar: November 8
4 | Execute test and logs bug | bar: November 10
2019-01-04 | News | 20130242 Nguyễn Văn Giang | bar: November 10
2019-02-04 | Product Search | 20130222 Cao Thành Đạt
2019-03-04 | Product Information Viewing | 21130371 Trần Minh Hướng
2019-04-04 | Payment/Order Placement | 20130452 Nguyễn Xuân Thành Trung
2019-05-04 | Shopping Cart | 19130031 Nguyễn Hoàng Đạt
2019-06-04 | Review | Team | bar: November 22
5 | Evaluting exit criteria & Test report | Team | bar: November 24
2024-01-05 | Check, adjust, and finalize the summary | Team | bar: December 21
6 | Review | Team | bar: December 28